## Sheet1
Component | Sub Component | Task | Estimate Hours
Header | Logo | add link | 0.1
Header | Logo | Hover effect | 0.2
Header | Social Links | Add CSS font icons | 1
Header | Social Links | add links | 0.1
Header | Social Links | Hover effect | 0.2
Header | Portfolio-DDL | Style open ddl button | 0.5
Header | Portfolio-DDL | Hover effect ddl button | 0.5
Header | Portfolio-DDL | Click style | 0.2
Header | Portfolio-DDL | Click functionality | 1
Header | Portfolio-DDL | Open/close animation | 1.5
Header | Portfolio-DDL | Hover effect ddl item | 0.5
Header | Portfolio-DDL | DDL item layout | 1.5
Header | Portfolio-DDL | Retrieve data from server | 0.5
Header | Portfolio-DDL | Server side service | 0.5
Header | Portfolio-DDL | DB data table | 0.5
Header | Blog btn | Style button | 1
Header | Blog btn | Hover effect | 0.5
Header | Blog btn | Click effect | 0.5
Bio | Description | Write text | 1
Bio | Description | Style text | 0.5
Bio | Description | Get text from server | 0.5
Bio | Description | Server side service and DB task | 1
Bio | Picture | Style picture | 0.5